## Sheet1
Engineer work hours | assuming 9 hours/ day and 5 days / week
Team work hours | 45 hours / day assuming working hours is divided equally between the team which means 900 hours / month | Time | Planned Value | Earned Value | Actual Value
Project Budget = | 10000 hours | 0 | 0 | 0 | 0
Project Duration = | 10000/900 =~ 12 months | 3 | 2500 | 2500 | 2500
|  | 6 | 5000 | 5500 | 7000
After 6 Months |  | 9 | 7500 | 8500 | 9000
Planned Value | 5000 hours | 12 | 10000 | 10000 | 12000
Earned Value | 55% of progress = 5500 hours
Actual Value | 7000 hours
Project Over Budget ? | Yes, by (7000-5500) = 1500 hours
Project Delayed ? | No, the project is early by 500 hours