## Sheet1
Risks | Probability | Impact | Planing Strat. | Action
deadline may be missed | L | H | transfer | ask sponsor or CEO for more developers
server down | M | H | mitigate | propose to buy UPS system
training not enough | M | M | mitigate | ask to extend training period